## Action Items Log
Action Items & Work Hours Tracking Log
# | Date | Day | Hours | Task / Activity Description | Status
1 | 2026-08-26 | Wednesday | 6.5 | Updated the “Build My Workflow / Run a Huddle” landing page. | Completed
2 |  |  |  | Removed dark mode functionality completely from the application. | Completed
3 |  |  |  | Added a clear navigation option to return to the Huddle landing page. | Completed
4 |  |  |  | Renamed “Onboarding” to “Orientation” across the application. | Completed
5 |  |  |  | Updated the PPT export/download feature so that clicking it displays a “Currently Unavailable” message instead of downloading a PPT file, until the PPT export functionality is ready. | Completed
6 | 2026-08-27 | Thursday | 30 min | Implemented a back-navigation option on the Huddle page. | Completed
7 |  |  | 45 min | Added a “Share Your Experience” field under the Overview section on the Generate Huddle page, retaining the existing questions currently used in the HTML export file. | Completed
8 |  |  | 30 min | Updated references from “Onboarding” to “Orientation” throughout the application. | Completed
9 |  |  | 1hr | Redesigned the main home page layout. | Completed
10 |  |  | 20 min | Updated the application name to “Frontier Accelerator.” | Completed
11 |  |  | 20 min | Updated the PPT export functionality to display a “Currently Unavailable” message instead of downloading the mock PPT file. | Completed
12 |  |  | 30 min | Renamed the application to “Frontier Accelerator App” across relevant screens. | Completed
13 |  |  | 1hr | Redesigned the layout page. | Completed
14 |  |  | 1hr | Updated the Frontier logo on the layout page. | Completed
15 | 2026-09-01 | Tuesday | 30 min | Adjust layout spacing across the application. | Pending
16 |  |  | 45min | Fix the clipped “W” display issue in the “Welcome” text on the Role Selector page. | Pending
17 |  |  | 1hr | Updated the Frontier logo across the application with the new logo. | Completed
18 |  |  | 4hrs | Researched the new data sheet and updated the database with the new data. | Completed
19 | 2026-09-02 | Wednesday | 2hrs | Created a new folder containing all data scripts for easier sharing. | Completed
20 |  |  | 2hrs | Resolved the workflow roles issue by removing duplicate roles based on the workflow module filter. | Completed
21 |  |  | 1hr | Updated the “Build My Day” page UI. | Completed
22 |  |  | 1hr | Removed duplicate role projections on the Workflow main page. | Completed
23 |  |  | 1hr | Updated the “Build My Day” page to support Day, Week, and Monthly view phases. | Completed
24 | 2026-09-03 | Thursday | 7 | Fixed the missing “HTML Downloaded Successfully” confirmation message after export. | Completed
25 |  |  |  | Replaced all external Unsplash image URLs with locally hosted assets bundled within the React/Vite application. | Completed
26 |  |  |  | Reviewed the frontend against the Web Resource Standards, identified compliance issues, and recommended cleanup actions. | Completed
27 |  |  |  | Implemented SSRF/AntiSSRF protection (WI-02) for the AITO backend: a. Integrated the Microsoft-approved Microsoft.Security.AntiSSRF NuGet package (v1.0.0) into the existing outbound HttpClient configuration. b. Applied AntiSSRF protection to all three Microsoft Graph HttpClient instances. c. Prevented requests to loopback, localhost, private, link-local, metadata, and other internal IP ranges. d. Added automated tests covering 169.254.169.254, 127.0.200.8, ::1, localhost, private IP ranges, and other required malicious destinations. e. Added redirect tests to ensure redirects cannot bypass SSRF validation. f. Verified legitimate Microsoft Graph requests to https://graph.microsoft.com/v1.0/ continue to work. g. Verified bearer tokens are sent only to trusted destinations. h. Ran the complete backend build and test suite and documented the results. i. Collected and provided the required outbound network/egress-filtering and CodeQL evidence for WI-02. | Completed
28 | 2026-09-04 | Friday | 7 | Removed “HealthDiagnosticPage.tsx” and “ReferenceDataDiagnosticPage.tsx” along with their unused dependencies and references. | Completed
29 |  |  |  | Removed the “reference-data-diagnostics” testing route and secured “ExceptionHandlingMiddleware” to prevent internal error details from being exposed. | Completed
30 |  |  |  | Fixed HuddlePlanApiTests failures caused by HuddlePlacement sequence and placement-mapping changes. | Completed
31 |  |  |  | Fixed 4 failing backend integration tests caused by a ConflictException: “No Role Path is configured for role 'role-1'.” | Completed
32 | 2026-09-07 | Monday | 8 | Added approved TypeScript security analysis (WI-06) using eslint-plugin-security and remediated the findings. | Completed
33 |  |  |  | Added approved C# security analysis using Roslyn security analyzers/DevSkim and remediated the findings. | Completed
34 |  |  |  | Verified that certificates are not improperly shared across Dev/UAT/Prod security contexts. | Completed
35 |  |  |  | Investigated the current OpenAPI configuration (WI-03) and determined how a valid OpenAPI JSON artifact can be generated for URSA without exposing Swagger UI publicly in Production. | Completed
36 |  |  |  | Investigated the approved ADO Manifest/SBOM Generator requirement and determined how an SPDX SBOM should be generated for the application. | Completed
37 | 2026-09-08 | Tuesday | 6 | Audited all API controllers and endpoints for proper server-side authorization. (Workitem-8) | Completed
38 |  |  |  | Verified ownership checks to prevent IDOR/BOLA vulnerabilities. | Completed
39 |  |  |  | Reviewed the Manager, Facilitator, and Team Member roles to determine whether they represent security roles or UX personas. | Completed
40 |  |  |  | Verified whether the Launch Planner requires Manager-only backend authorization. | Completed
41 |  |  |  | Reviewed the HealthController and confirmed whether unauthenticated access is intentional. | Completed
42 |  |  |  | Implemented the authorization/ownership changes identified during the audit. | Completed
43 |  |  |  | Investigated and removed the unused HealthController and related database health-check functionality, and cleaned up its frontend/API references and documentation without affecting unrelated project functionality. | Completed
44 | 2026-09-09 | Wednesday | 20 min | Added the FluentValidation implementation directly in the repository; this code needs to be pulled to the local system. | Completed
45 |  |  | 30 min | Added the “Backend/**/appsettings.json” pattern to the global .gitignore file to prevent appsettings.json files from being tracked. | Completed
|  |  | 2hrs | React Learnings
46 |  |  | 3hrs | Deployed the application on the client's side. (3 hrs) | Completed
47 | 2026-09-10 | Thursday | 3hrs | Completed React learnings covering JSX and Components. (3 hrs) | Completed
|  |  | 3hrs | Investigated W-12 (MISE Integration). | Completed
49 | 2026-09-11 | Friday | 30 min | Fixed a UI visibility issue on the Role Selector page where the “Welcome” text was partially clipped (the “W” was cut off); investigated and corrected the spacing/positioning so the complete “Welcome 👋” text displays correctly without affecting the existing layout or decorative background elements. | Completed
50 |  |  | 30min | Removed the “My Workflows” navigation option from the top layout while retaining all existing My Workflows functionality. | Completed
51 |  |  | 30m in | Updated the Layout Bar profile section to dynamically display the currently logged-in user's name instead of the default “User” label. | Completed
52 |  |  | 30 min | Added a back button to the My Workflows/Saved Workflows page so users can return to the previous Activity Selection page. | Completed
|  |  | 2hrs | Investigated approach for MISE Implementation.
53 |  |  | 30min | Aligned the Workflow/Huddle mode switcher position so it remains horizontally consistent and does not shift when switching between modules. | Completed
54 | 2026-09-15 | Tuesday | 3hrs | Completed learning on SQL Indexing. (3 hrs) | Completed
55 |  |  | 2hrs | Investigated PR (pull request) issues. (2 hrs) | Completed
56 |  |  | 30min | Renamed “Additional Topics” to “All Topics” throughout the application. (30 min) | Completed
57 |  |  | 1hr30min | Applied the W-12 and related UI changes and pushed the updated repository to the client's side. (1 hr 30 min) | Completed
58 | 2026-09-16 | Wednesday | 1hr | Planning notes – Current Priorities: work on the latest data scripts; resolve test-case failure issues. Parked Items: project content across all topics; replace Huddle pop-up design; build “A Day” UI; add Huddle feature tips; fix spacing for single-line topic descriptions; remove W1 for teammates. | Note
59 |  |  | 2hrs | Worked on the new data sheet and generated new data scripts. (2 hrs) | Completed
60 |  |  | 1hr | Updated the existing data with the new data. (1 hr) | Completed
61 |  |  | 1hr | Resolved test-case failure issues in the externalResources.test.ts file. (1 hr) | Completed
62 |  |  | 2hrs | Listed all endpoints and generated a document for use by the URSA Scanner. (2 hrs) | Completed
63 | 2026-09-17 | Thursday | 3hrs | Investigated the new data sheet, updated the database with the new data (V5), generated new data scripts for the updated data, and updated the “fresh-install-v11.2.6” folder. (3 hrs) | Completed
64 |  |  | 30min | Fixed the Audience dropdown height to match other Huddle filters. (30 min) | Completed
65 |  |  | 2hrs | Investigated why Sales Home/Deal Home are being projected as Primary Agents for Enterprise roles through shared topics, and analyzed the workbook and application mapping to determine whether the issue is caused by topic-level agent mapping, along with the appropriate next steps. | Completed
66 |  |  | 50min | Attended a deployment meeting with Nihar. (50 min) | Completed
67 | 2026-09-18 | Friday | 7 | Fixed Role/Segment-Scoped Primary Agent Projection – investigated and corrected the Primary Agent mapping to use activities associated with the selected Role Path/segment instead of the shared Topic-Agent mapping, while displaying all distinct Primary Agents from relevant activities and preserving existing shared Topic-Agent mappings. | Completed
68 |  |  |  | Reverted the MISE integration for local development – restored “Microsoft.Identity.Web” inbound authentication without modifying any unrelated application changes. | Completed
69 |  |  |  | Updated the HTML export UI/UX based on the provided mockup – redesigned the HTML export layout and styling to align with the In-App Data mockup while preserving existing functionality. | Completed
70 |  |  |  | Fixed right-side card scrolling behavior on the Role Path page – updated the Huddle page so the right-side card remains visible while scrolling through topics, without affecting other UI/UX or functionality. | Completed
71 |  |  |  | Synchronized In-App Data Huddle features with the updated working repository – updated the Huddle components, UI/UX, exports, and supporting functionality to align with the latest working repository while preserving the standalone static/in-memory architecture. | Completed
72 |  |  |  | After integrating MISE packages into the Agentic AI Feed, encountered 6 pipeline issues; resolved all of them and integrated the required Huddle changes without introducing backend, database, Azure, or Graph API dependencies. | Completed
73 |  |  |  | Generated a dist file containing the in-app data and all updated features. | Completed
74 | 2026-09-21 | Monday | 1hr | Resolved pipeline issues. | Completed
75 |  |  | 2hrs | Completed User Data Storage Remediation – removed stored user PII (OwnerEmail, OwnerDisplayName) and cleaned up the unused WorkflowShares implementation while retaining OwnerObjectId. (2 hrs) | Completed
76 |  |  | 45min | Upgraded the MISE version from 2.0.1 to 2.5.1 and updated the code accordingly. (45 min) | Completed
77 |  |  | 2hrs | Investigated the pipeline NuGet restore failure introduced after adding Microsoft.Identity.ServiceEssentials.AspNetCore 2.5.1, specifically the unresolved Microsoft.Identity.ManagedCertificates dependency from AgenticAICodeFeed; identified the dependency/feed configuration issue, coordinated with the tech team, and resolved the package restore issue so the pipeline build completes successfully. (2 hrs) | Completed
78 |  |  | 1hr | Resolved Frontend ESLint errors – fixed the 13 blocking ESLint errors in the frontend while preserving existing functionality, UI behavior, and architecture, without modifying the backend or ESLint/package configuration; ran npm run lint and npm run dev after the fixes, achieving 0 ESLint errors while retaining existing warnings. (1 hr) | Completed
79 |  |  | 2hrs | Updated the Azure repository with ESLint fixes, data-fetching updates, Role Path Card implementation, database schema changes, and Primary Tool projection fixes. (2 hrs) | Completed
80 | 2026-09-22 | Tuesday | 30 min | Updated stale Huddle export test assertions – changed the outdated test expectations from “tool” to “closing” and from “1 optional” to “1 extended.” (30 min) | Completed
81 |  |  | 30 min | Fixed inconsistent font stack in the Huddle HTML export – replaced the remaining hardcoded font declarations with the shared HUDDLE_FONT_STACK constant. (30 min) | Completed
82 |  |  | 3hrs | Updated the HTML export (3 hrs), including: a. Removed the Facilitator Notes section. b. Fixed the Sales Agent logo rendering outside its container. c. Removed the white background from the Researcher & Agent J logos so they appear transparent, consistent with other logos. d. Updated logo highlighting to reflect the Top 5 agents for each topic (e.g., displaying Cowork and Scout in the Top 5 band, with the expected blue highlight background). e. Ensured that an activity's Top 5 agents are listed under “Top 5” in band order, with the remaining agents moved under “Also Used.” f. Updated the “Share Your Experience” section to present points in a straight line, one after another, per the provided reference. (30 min) g. Updated the Preparation Conversation Guidance feature. (30 min) | Completed
83 |  |  | 1hr | Resolved the MISE pipeline issue. (1 hr) | Completed
|  |  | 1hr | Resolved the authorizationpolicytests.cs integration test failures. (1 hr)
84 |  |  | 1hr | Replaced all the feature files with the latest changes to the repo (Buiuld Successful) | Completed
85 | 2026-09-23 | Wednesday | 1hr | Reviewed the Azure SQL Database schema and data structure based on the Code First implementation and updated database scripts. Created a client-facing document covering the schema, entity relationships, data overview, and representative sample records. | Completed
86 |  |  | 1hr | Reviewed Privacy Questions and answers. | Completed
87 |  |  | 40 min | Bi-Weekly meeting | Completed
88 |  |  | 3hrs | Made updates to the in-app data. (update all the changes to app in data which resembles the main app) | Completed
89 |  |  | 1hr | Updated the HTML export. | Completed
90
91 | 2026-09-24 | Thursday | 30 min | Home page:Update Run a Huddle Card Color to Blue (in both in-app and main app) |  | done
92 |  |  | 30 min | Task: Clean up unwanted text in the `DisplayLabel` column of "dbo.HuddleActivityAgents", including `, "Surfaced through Sales Agent" and `(Sales Agent)`. Scope: Update only "DisplayLabel", preserve all other data unchanged, and preview affected records before applying the update. (In main app) | in main app | done
93 |  |  | 30 min | Update DisplayLabel values in the in-app data file and HuddleActivityAgents table by removing unwanted text while preserving the original agent names.Modify only the DisplayLabel values and leave all other data, structure, UI, functionality, and application logic unchanged. | in In app | done
94 |  |  | 30 min | Task Name: Enable Single-Click Role Selection and Navigation to Choose Activities..in workflow role selctor page. (in app) | both in in-app and main app | done
95 |  |  | 20 min | Task Name: Update fresh-install-v11.78 Data Script for HuddleActivityAgents DisplayLabel Cleanup (main app)
96 |  |  | 30 min | Task: Fix the All Topics Audience dropdown to support selecting/deselecting individual options and the Clear option, without modifying any other features or UI behavior. (in app) (main app) |  | done
97 |  |  | 20 min | Task Name: Implement Role Path Topic Select/Deselect Toggle with Side Panel Behavior..(role path page) (in app & main app) |  | done
98
99 |  |  | 20 min | Task Name: Fix Side Panel Behavior When Deselecting Topics on the "All Topics" Page | In App | done
100 |  |  | 1hr30min | Reviewed Privacy Questions and answers. (document)
101 |  |  | 10 min | Make side headings bold (in app and main app) |  | done
102 |  |  | 1hr | Update the All Topics page to show All Topics + applicable Role Path topics by default, filter Role Path topics by selected Audience, and add an “Only All Topics” option to show only the 19 All Topics topics. (in-app & main app) |  | pending
103 |  |  | 30 min | Currently, some applicable agents such as "Sales Home are not being identified or displayed under Primary/Secondary Tools and the Resources tab", and the task is to investigate why this is happening across roles/topics and fix the underlying mapping/filtering issue. (in-app) |  | pending
104 |  |  | 5 mins | Remove logo in the html page
105 | 2026-09-25 | Friday | 30 min | Remove the “All Roles” option from the Role Path page while keeping it available on the All Topics page. (in-app). | need to implement in main app | done
|  |  | 15 min | Hide the Notifications icon from the UI until its notification functionality is fully implemented and ready for use. (in-app & main app). |  | done
start from here
|  |  | 1hr | Restore and organize the Export Learning Plan code so the downloaded file matches the previous expected UI, while modifying only export-related code . (in-app & main app) (need to check o/p in main app)
|  |  | 1hr | Fix Role Path Missing Weeks and Topic Mapping Issues: Fix the identified Role Path data/mapping issues for DSE, DCSA, and PSS using the Excel as the source of truth, resolve the DSE TopicID collision, verify SSP sequencing, and ensure the correct weeks/topics display without affecting any other features. (in -app)
|  |  | 1hr:30 | Correct the main application database `HuddlePlacements` data by updating the four affected Role Path records ("DCSA-CONSUME", "DSE-ARCH","PSS-JOINTPLAN", and "PSS-PARTNER") to their correct "PathSection" and "Sequence" values so DCSA Week 2, DSE Week 3, and PSS Weeks 2–3 display correctly without affecting any other data. (main app) (need to check) | need to check
|  |  | 20 min | update "fresh-install-v11.78" folder based on the above change (main app database folder)
|  |  |  | Implement SME&C audience role descriptions by reading the existing role description data and displaying the corresponding description alongside each SME&C role in the Audience dropdown, consistent with how descriptions are shown for the other roles. (description) | pending
|  |  |  | Task Name: Add Weekly Pulse Instruction to Closing and Next Steps Section in html page (in-app & main app) | done
|  |  | 20 min | Closing & Next Steps section now: (in-app) Stage-header subtitle: "Close the loop on today's Huddle, capture the manager reflection, and take a quick weekly pulse." Weekly Pulse card: "Rate this week's Huddle before you close." (plain text) followed by the existing bold rating question — matches your second marked line, already correct from before. | pending in main app
|  |  | 20 min | Move the "Workflow and Huddle buttons closer to the app name/logo", using the empty space available after the logo, without changing their design or functionality. (in-app & main-app)
| 2026-09-28 | Monday | 1 hr 30 | Investigate the root cause of incorrect Role Path topic mappings and implement the required database mapping changes so existing topics are displayed under their correct weeks. (MAIN APP)
|  |  | 1hr 20 m | The right-side Huddle panel is not positioned correctly based on the selected week, requiring users to scroll to the top or bottom to access it and its actions. Update only the panel’s scrolling/positioning behavior so it follows the selected week while "preserving all existing features and functionality" such as Generate Huddle, HTML, Meet with a Coach, and the three-dot menu. (main-app & in-app)
|  |  | 2hrs | Practical Implementation of JSX and Components in My POC
|  |  | 40 min | Investigation on using user.read v/s profile for fetching basic information.
|  |  | 40 min | call
|  |  |  | Task: Fix All Topics Side Panel Behavior on Topic Deselection In the All Topics page, users can select multiple topics, and the side panel should display the details of the currently selected topic. The current issue occurs when multiple topics are selected and the user starts deselecting them. After deselecting a topic, the application incorrectly treats the deselected topic as selected again and displays its related side-panel content. The side panel should only be driven by topics that are currently selected. When a topic is deselected, it must not reopen or remain as the active side-panel topic. If no topics remain selected, the side panel should return to the existing “Select a Huddle”state. Fix only this selection/side-panel synchronization issue in the All Topics page, without modifying any other functionality, UI, data, backend behavior, or unrelated files. (in-app) | (check the status in main app.)
Update the **All Topics** projection from the current 27 unique-topic deduplicated view to use the same placement-level projection logic as Role Path, so all applicable role/placement-specific topic projections from the 138 `HuddlePlacements` rows are represented while preserving existing filters, selection, side-panel behavior, UI, and all unrelated functionality.
|  |  | 1hr | Meet 1hr
|  |  | 1hr | Organize the udpated data scripts folder and push that folder into the client's repository.
Create a data flow diagram for our current application
|  |  | 10 min | The Reset and Export Learning Plan buttons were previously displayed side by side, but now the Export Learning Plan button is appearing below the Reset button.Please fix this issue by placing both buttons side by side, as they were earlier. (in-app) in recommendedCardPath.tsx (RolePath Page)
|  |  |  | when i choose "replace huddle" option in role path page. why it is showing the same topic these many times. resolve that (in-app) | check in main app
|  |  |  | Task Name: Huddle Agent Icon Updates Update the Huddle page to display the newly added GitHub Copilot and MSXI Agent logos and remove the default fallback logo for agents without an available icon, without affecting any other functionality. | In App;check the status in main app
| 2026-09-30 | Wednesday |  | Task: Update the current "Meet with a Coach" experience to display a simple “Coming Soon” message when clicked, while keeping the existing Coach integration and functionality intact for the planned V2 release and making no other UI or code changes. | need to update this feature in main app.
|  |  |  | Task: Fix Independent Topic Selection on All Topics Page— Currently, selecting one topic automatically selects another topic; update the selection logic so each topic can be selected/deselected independently while keeping the existing multi-select functionality and all other UI/features unchanged. | Validated in both in-app & main app.
|  |  |  | Task: Fix Build Learning Plan Topic Heading Projection Currently, Build Learning Plan displays the Topic Name instead of the corresponding Role Topic Name (`roleTopicName`); update the projection to use `roleTopicName` so the headings match the "All Topics" page, without changing any other feature or UI. | implemented in both in app & main app.
|  |  |  | Task:Fix the Role Path topic highlighting issue by correcting the selection/highlighting logic, validate it across all roles, and make only the minimal UI-related changes without affecting other features or files. (for AE:if I select week 3 topic week 4 is also highlighting) | Need to implement in main app. |  | prompt in chat
|  |  |  | Need to work on data part (I found same topic appears in multiple week places in the in-app role path page Task: Correct the Role Path role → week → topic data mapping using the updated Excel as the source of truth, trace and fix the underlying duplication/mismatch, and validate all roles without modifying any unrelated UI, functionality, or files.) | only in in app modify the data.
|  |  |  | Task Name:Make Week 1 Common for All Roles Use one shared Week 1 data object with the common heading and description for all roles, while keeping all other Week 1 fields, Weeks 2–8, UI, and functionality unchanged. | need to implement in main app |  | in-app prompt in teams chat | pending
|  |  | 2hrs | WORKED ON HUDDLE IN A BOX FEATURE
| 2026-09-01 |  | 6hrs | Investigate alternatives to the current `access_as_user` scope approach, as obtaining the required client/admin consent is expected to take around 3 months. Explore and evaluate alternative authentication approaches that can allow the application to go live sooner while maintaining the required application functionality.
Investigate the current access_as_user authentication, APIM, Private App Service, and Microsoft Graph/OBO flow, and identify the limitations with the current approach. Explore alternative architectures such as SWA → APIM → Private App Service and determine the best feasible approach that can address the current authentication/consent issue without breaking existing functionality.
2026-09-05
| 2026-09-06 |  | 40 min | Gone through video to understand the requirements
| 2026-09-06 |  |  | 3. Rename the Step 01 card from "Onboarding" to "Onboarding / Orientation" so users understand what this step is for. | done in both in-app & main app. |  | done
|  |  |  | Remove the “Effort” section from the three cards under “One motion. Three connected steps” and professionally reorganize the remaining card content without affecting other pages or components. In HuddleOnboardingExperience.tsx file. | verify in main app |  | done
|  |  |  | Remove Step 6 – “Join your first huddle” from the “Before you begin” section of the onboarding page without affecting other features. b.Simplify the "Readiness Checklist" by replacing “Complete AI Fundamentals” with “Top 5 MCAPS Agents Training” and combining it with "Recommended Resources" to reduce the checklist to approximately four items. | verify in main app |  | done
|  |  |  | Update the "Huddle Details panel" by placing the "HTML" button at the top and "Generate Huddle" below it, while preserving their respective styling and existing functionality. | verify in main app |  | done
|  |  | 1hr | Swap the “What brings you here today?” and “Top 5 Agents” sections, reorganize the Top 5 Agents into a spacious 2-column layout, and fit all agents within the existing card space without increasing the overall section height. | need to implment in main app
|  |  | 1hr | Renamed and repositioned "Generate Huddle" as a "Facilitator-specific experience", with a subtle CTA and appropriate access flow for different user roles. | verfiy in main app |  | done
| 2026-10-07 | Wed | 1hr 30 | Resolved Merge conflicts.
|  |  | 45 min | Fix the issue where a topic selected under Manager remains selected in All Topics after switching to the Facilitator role. (All Topics Page) (drop down and topic issue) | need to verify in in-app
|  |  |  | Fix the issue where a topic selected under one Audience remains highlighted after clearing or changing the Audience filter, causing incorrect topic selection across different audiences. | need to verify in in-app
|  |  |  | Task Name: Fix Side Panel Behavior When Deselecting Topics on the "All Topics" Page.currently if you select one topic and deselct it it is showing the side panel. Fix that in case of selecting multiple topics | already implemented in in-app now implemented in main app |  | done
|  |  |  | Remove the “All Roles” option from the Role Path page while keeping it available on the All Topics page. | implemented pending item in main app |  | done
|  |  | 1hr | All Hands meeting
| 2026-10-08 |  |  | Investigated the entire pipeline code developed by tech team
| 2026-10-09 |  | 1hr | Audited and enhanced the existing Tips/Walkthrough feature to identify and implement missing, outdated, and broken tips across pages, buttons, cards, and workflows, ensuring accurate guidance for new users and role-specific features. | verify in main app
|  |  | 2 hr 30 | meet with nihar regarding Sandbox database
|  |  | 1hr | Investigated CD pipeline code
|  |  | 2 hr 30 | SQL learnings on QUERY & OPTIMIZATION
| 2026-10-12 |  | 4hrs | SQL learnings on QUERY & OPTIMIZATION (Practical Implementation)
|  |  | 3hrs | implemented main app changes
|  |  |  | Extended the existing guided walkthrough to include Step 6 – Profile Settings & Feedback, highlighting the profile menu and Send feedback option while preserving all existing features and functionality. | verify in main app
| 2026-10-13 |  | 2hrs | learnings
|  |  | 2-4:50 | meet with nihar regarding Sandbox database
|  |  | 5:30-6:30 | meet with nihar regarding Sandbox database,ran cd pipelines for qa environment
| 2026-10-14 |  |  | answering questions of privacy review
|  |  | 1 hr 30 | created a data flow diagram for our application
meet with brahmam
|  |  | 30 min | Validated client's generated data flow diagram.
|  |  |  | The current walkthrough displays the “Create your own huddle” tip as the second step, while essential navigation and page-orientation guidance need higher priority. Reordered the tips to show essential guidance first and moved the huddle creation tip to the final step, removing unnecessary tips without affecting other features. | need to implement in main app | prompt in team's chat
Updated the Facilitator Hub to display Primary AI Tools and Secondary AI Tools in separate sections instead of combining them under Key AI Tools. Ensured tools are categorized using existing application data while preserving other features and UI functionality.
| 2026-10-15 |  |  | Compared the existing application data with the newly provided Excel workbook to identify missing, outdated, mismatched, and additional records. Updated the application data file and made the necessary UI and data-mapping changes to align the application with the new workbook while preserving existing functionality.
|  |  |  | Huddle segment and role updates are also appearing in Workflow Builder, which should retain only its original Enterprise and Manager segments. Expected behavior: Keep Workflow and Huddle role lists separate so changes in one module do not affect the other, without breaking existing functionality. | need to implement in main app
**Task: Update Five Incorrect Huddle Role Path Placements Using the Latest Excel Workbook** **Current Scenario:** The AITO Huddle Generator application is displaying older or incorrect placement content for five role/week combinations. The latest workbook, `Frontier_Accelerator_Huddle_App_Content_Integration_Model_10.13.2026 v2.xlsx`, contains the updated placements, but these placement IDs and their corresponding content are missing from the application's runtime data and role/week mappings. The affected placements are `DAE-W06`, `CE-W02`, `CE-W07`, `DSE-W06`, and `DCSA-W02`. Although the corresponding weeks are visible in the application, they display older placements or different titles instead of the latest workbook content. **Required Fix:** Update the application's runtime data and relevant role/week mappings using the exact content from the workbook's `Role_Paths` sheet. Ensure that each placement is associated with the correct role and week and that the UI displays the updated title, description, objective, WIIFM text, and other required fields. Validate the changes against the workbook and verify that all five placements display correctly in the application. Preserve existing functionality, keep Workflow Builder and Huddle Generator roles separate, and avoid modifying unrelated data, features, or files.
Currently, 19 resources in the Excel workbook are not linked to any topic or activity, so they are not easily accessible through the Huddle page. Update the existing Resources button to display these resources globally for all roles, without changing any other features.
Task Name: Fully Synchronize AITO Huddle Generator Data with the Latest Excel Workbook: Synchronize AITO Huddle Generator data with the latest Excel workbook, updating outdated topics, activities, placements, DSS content, and role/week mappings while removing obsolete records. Validate all changes against the workbook and run available tests and builds. Keep changes limited to Huddle data and required runtime logic, preserve unrelated functionality, and do not commit or push changes.
| 2026-10-16 |  |  | Task Name: Fix Huddle Tool Mapping Logic to Use Activity-Level Assignments
Issue
Currently, the application uses a combination of activity-level and topic-level mappings to display AI tools for a specific role-path week. Primary tools are fetched from activity-level mappings, while Secondary tools are fetched from topic-level mappings. This can cause tools that are associated with a topic generally, but are not assigned to that specific huddle's activities, to appear in the UI.
Existing Mapping Logic
Role_Paths: Identifies the role, week, and associated topic/placement.
Activities: Provides the activities associated with the selected placement.
Activity_Agents: Maps each Activity ID to its assigned Agent ID and usage type (Primary or Secondary).
Topic_Agents: Stores topic-level tool mappings, which may include tools not assigned to the selected huddle's activities.
Agents: Maps Agent IDs to readable tool names.
Previously, the application fetched Primary tools from Activity_Agents but fetched Secondary tools from Topic_Agents. As a result, unrelated topic-level tools could appear as Secondary tools for a specific role-path week.
Implementation
The tool-mapping logic has been updated in the Standalone application to use Activity_Agents as the source for both Primary and Secondary tools. The application identifies the activities belonging to the selected placement and retrieves their assigned tools and usage types from the activity-level mappings.
This ensures that both Primary and Secondary tools are based on the activities assigned to that specific role-path week, rather than including tools simply because they are associated with the broader topic.
Remaining Work
Apply the same mapping-logic change to the main application (.NET backend and SQL Server). Update the backend logic so that both Primary and Secondary tools are derived from activity-level assignments in Activity_Agents/the corresponding activity-agent database mappings, instead of deriving Secondary tools from topic-level mappings.
Expected Result
Both the Standalone and main applications should display tools consistently and only use activity-level assignments for the selected role-path placement. Topic-level mappings in Topic_Agents should not independently introduce tools into the huddle's Primary or Secondary lists.
| 2026-10-22 |  |  | Worked on UAT DEPLOYMENT PROCESS.
| 2026-10-26 |  | 1hr | Meet with nihar regaring prod deployment
|  |  | 3hr 30 mi | claude assessment
|  |  | 1hr | Revised claude workshop concepts
|  |  | 45 min | worked on merge conflicts and shared new updated zip file
2026-10-27
Note on B50: Ganesh Chaturthi – Regional Holiday
Note on B90: Date corrected from “2024” to “2026” in the original file (evident typo).